{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":30,"n_cols":8,"rows_kept":30,"merged":[[1,1,1,7],[3,1,4,1],[3,2,4,2],[3,6,4,6],[3,7,4,7],[5,1,7,1],[5,2,7,2],[10,0,11,0],[16,1,18,1],[16,2,18,2],[16,4,18,4],[16,5,18,5],[16,6,18,6],[19,1,21,1],[19,2,21,2],[22,1,24,1],[22,2,24,2],[23,0,24,0],[25,0,26,0],[26,1,29,1],[26,2,29,2]]}
[null,"附件"]
[null,"交城县大气污染综合治理攻坚任务分解清单"]
[null,"序号","任务","细化任务","牵头  县领导","责任单位","配合单位","时间节点"]
[null,1,"严把项目准入","经济开发区审批项目","陈向东","经济开发区","市生态环境局交城分局、县自然资源局、县应急管理局、县能源局、县水利局","长期坚持"]
[{"$nulls":3},"行政审批局审批项目","李旭东","县行政审批局"]
[null,2,"淘汰落后产能","未完成超低排放改造的焦化、钢铁、水泥企业和长期存在异味污染和安全隐患未得到有效治理的有机化工企业","王向前","市生态环境局交城分局、县应急管理局","县工信局","6月底"]
[{"$nulls":3},"环保绩效评级达不到C级的铸造企业和达不到B级的砖瓦企业","王向前","市生态环境局交城分局","县工信局","10月底"]
[{"$nulls":3},"《产业结构调整目录（2024版）》要求淘汰的设备和生产工艺","王向前","县工信局","市生态环境局交城分局、县应急管理局","按要求的时序进度"]
[null,3,"产业集群提升","对标行业先进水平，对我县玻璃制品、硝基盐、铸造三大产业集群进行治理提升，提高产业集中度和绿色发展水平。","王向前","市生态环境局交城分局",null,"10月底"]
["- 11 -",4,"加强园区整治","按照《交城经济开发区生态环境综合治理行动方案》（交发〔2024〕1号）文件精神，以建设“绿色、低碳、创新、开放、活力”型经济开发区为目标，举全县之力，高起点、高标准打造绿色、生态、低碳的花园式经济开发区，建设全省生态工业园区样板。","陈向东\n王向前","经济开发区、市生态环境局交城分局","其他相关单位","按要求的时序进度"]
["- 12 -","序号","任务","细化任务","牵头  县领导","责任单位","配合单位","时间节点"]
[null,5,"严格控制煤炭消费总量","6月底前淘汰红星化工35蒸吨/小时和华鑫肥业75蒸吨/小时备用燃煤锅炉。10月底完成农业和养殖业燃煤锅炉生物质替代。","王向前\n张  杰","市生态环境局交城分局、县农业农村局",null,"按要求的时序进度"]
[null,6,"推进工业炉窑清洁能源替代","推进工业炉窑清洁能源替代，新改扩建工业炉窑应采用清洁能源，全面启动开发区耐火材料、陶瓷、铸造、炭素等行业工业炉窑清洁能源替代。","王向前","市生态环境局交城分局",null,"12月底前"]
[null,7,"平川区域散煤采暖清零","加快散煤清零工程建设，全面禁止销售、储存、使用散煤，年底前全面实现海拔900米以下散煤清零，平川区域1.18万户居民清洁采暖。加强对燃煤企业煤质检测和监管，杜绝劣质煤进入市场。","雒保廷\n王向前","县住建局、县能源局","市生态环境局交城分局、县市场局、各乡镇","12月底前"]
[null,8,"推进交通运输绿色清洁发展","实施交通运输绿色清洁发展行动，建设氢能制储加用一体化运营平台，实现短途运输车辆、厂内运输车辆绿色低碳，2024年底前新建2座加氢站，达到3座加氢站、300辆氢能重卡。积极推进“集装箱+新能源重卡”试点项目建设。加快推进非道路移动机械新能源化发展，开发区内新增或更新的作业车辆和机械力争使用新能源。2024年辖区内运输车辆新能源替代率要达到60%，2025年达到80%。建立健全部门联合执法体系，严厉打击超标、淘汰车辆上路行驶行为。","陈向东\n原瑞年\n王向前\n张  杰","经济开发区、市生态环境局交城分局、县交通运输局、县工信局、县交警大队",null,"12月底前"]
[null,"序号","任务","细化任务","牵头  县领导","责任单位","配合单位","时间节点"]
[null,9,"工业企业深度治理","异味污染综合治理","王向前","市生态环境局交城分局","县工信局、经济开发区、县供电公司","6月底"]
[{"$nulls":3},"提效升级行动",{"$nulls":3},"12月底前"]
[{"$nulls":3},"大气环境应急能力建设",{"$nulls":3},"12月底前"]
[null,10,"臭氧污染专项治理","5—9月份每日10时—16时，禁止户外涂装作业和建成区建筑墙体涂刷以及道路划线、栏杆喷涂、道路沥青铺装等户外涉有机废气的工程作业，除特殊功能要求外的室外构筑物防护和道路交通标志全面使用低挥发性有机物含量涂料。","雒保廷","县住建局","市生态环境局交城分局","5—9月份"]
[{"$nulls":3},"加油站要安装配套油气回收设施，并正常运行，5—9月份引导群众错时加油。","王向前","县工信局","市生态环境局交城分局","5—9月份"]
[{"$nulls":3},"餐饮油烟治理","雒保廷","县住建局","市生态环境局交城分局","5月底"]
[null,11,"扬尘污染专项治理","建筑施工工地扬尘污染治理","雒保廷","县住建局",null,"长期坚持"]
["- 13 -",null,null,"“散乱污”堆场治理","王向前","各乡镇、市生态环境局交城分局",null,"6月底"]
[{"$nulls":3},"裸露土地专项治理","王向前","各企业","县住建局、县自然资源局、各乡镇","6月底"]
["- 14 -","序号","任务","细化任务","牵头  县领导","责任单位","配合单位","时间节点"]
[null,12,"环境监管能力建设","新安装一处雷达扫描和两个高空视频，启用2个经济开发区和4个乡镇环境空气质量监测站点。","王向前","市生态环境局交城分局",null,"5月底"]
[{"$nulls":3},"实施全县排污单位电力监控设施全覆盖","王向前","市生态环境局交城分局",null,"年底"]
[{"$nulls":3},"交城县环境监管一体化管理平台运行","王向前","市生态环境局交城分局",null,"5月底"]
[{"$nulls":3},"完善执法机制","陈向东\n王向前","经济开发区、市生态环境局交城分局","相关单位","长期坚持"]